# Timeframes for Planning Permission

The timescale involved in obtaining planning permission (Table 1) depends on the validity of the application and if the local authority decision is appealed. There is a time limit of eight weeks from when a valid application is lodged to a decision being given by the planning authority.

The planning authority may issue a decision on the application (grant or refuse permission) or they may request further information.

If the Planning Authority request further information, they have four weeks from the day the further information is received to make a decision on the application (unless the application is accompanied by an Environmental Impact Statement, in which case, the time for making a decision is extended to 8 weeks).

Any appeal of the decision must be submitted within four weeks of the local authority decision to An Bord Pleanála who has an objective to decide appeals within 18 weeks of receipt.

Table 1: Timescale for most planning permission cases

| Stage | Timescale | Action |
| --- | --- | --- |
| Public Notices |  | Notice published in newspaper and site notice erected |
| Receipt of application | 2 weeks | Application must be lodged within 2 weeks of publication of newspaper notice. |
| Validation | 1 - 5 days | Application is validated by the planning authority as soon as possible. Current timescale is within 5 days. |
| Submissions | 5 weeks | Submissions/observations can be submitted within the first 5 weeks of receipt of application. |
| Notice of Decision | 8 weeks | Submissions/objections (submitted in first 5 weeks) are considered. Planning Authority (PA) issue notice of their decision on the application within 8 weeks of receipt of application. (Alternatively, they may request further information.) |
| Further Information | 6 months | The PA may request Further Information or clarification of Further Information which must be responded to within 6 months (this can be extended by 3 months at the discretion of the PA) |
| Notice of Decision | 4 weeks (8 weeks for EIS) | The PA issue notice of their decision on the application within 4 weeks of receipt of the Further Information. (Time period is extended to 8 weeks in the case of an application accompanied by an EIS) |
| Appeal | 28 days | A decision can be appealed to An Bord Pleanala within 28 days of a decision. |
| Final Grant Minimum | 4 weeks + 3 days | If the decision is not appealed to An Bord Pleanala, then the Planning Authority will issue a final grant of permission. |