Taste of Cavan Committee Meeting 24th October, 2016 @ 9.15am

Reference Room, Old Library

Present:  Alo Mohan (Chair), Eoin Doyle, Ger Finn, Caroline Brady, John Donohoe,  Eugene Kiernan, Gerry Sheridan, Majella Tierney, Conor Harrington, Winston Bennett, James Spears, Joanne Hayes

Apologies: Catherine Fox, Marcella Rudden, Ann Marie Lacey

- Food Strategy

Caroline Brady updated members on the Strategy – Bulls Eye Consultants from Cork were appointed and have recommended 4 key areas to work on – Support, Route to Market, Education and Food Tourism.  The Farmers Market will also be looked at within the Strategy.

It was agreed that the Draft Strategy would be sent to producers, members of Economic SPC and members of TOC committee.

- Review of Taste of Cavan 2016

There was discussion on what worked well and what didn’t and the committee will be mindful of this for 2017.

Budget/Sponsors - The cost of holding the event was discussed in detail.  There was discussion on admission fee of €5 and stand fees.  There was discussion on the level of sponsorship provided by the various sponsors.

Marketing Review/Consumer survey - Road signage, local media, Facebook, and personal recommendations are the main ways people hear about the Taste of Cavan.

Five per cent of visitors to the 2016 Taste of Cavan were not from Ireland. In 2016, of our Irish visitors, 71% were from Cavan and 29% from other Irish counties, with 7% of these from Northern Ireland. In 2015, 83% of visitors to the Taste of Cavan were from Cavan with 18% from outside of the County. Therefore, of the Irish visitors, the numbers of visitors from outside the county to the Taste of Cavan grew from 18% to 29% from 2015 to 2016.

In 2016, 47% of visitors were families with children.  In 2015, families made up 25% of visitors, giving an increase of 22% in families attending the show.   Twenty per cent of respondents at the show spent over €80. This demonstrates an increase in expenditure from 2015. Only 11% of respondents in 2015 spent over €80.

Le Cheile Cook Book for the Autism Unit raised a significant amount of money at the event. For 2017, the committee will review the charity rules.

- Taste of Cavan 2017

It was agreed by all that the Venue is excellent and that discussion should be commenced immediately with owners to get agreement on cost for 2017 and for further years.

There was discussion on dates and duration – it was agreed that the event would take place on 11/12th August (Tullamore Show is on 13th Aug) and that two days is sufficient from an exhibitor point of view and also in terms of needing many more volunteers to run the event for a third day.   Event will be monitored and if numbers attending dictate that 3 days are required from visitor comfort point of view, this will be considered.  We could consider asking more organisations to volunteer also.

We need to look at the overall plan for Taste of Cavan in terms of it being a Regional event and we need to balance producers while all the time keeping the standard very high.

Launch – Members discussed having the launch in another Cavan premises and that it would be good to rotate venue.  Another suggestion was to do something in Cavan Town.  Members are to think about suggestions for next meeting.

Membership of committee – there was discussion on whether the Chairman of the County Council and another producer should be invited onto the committee - it was agreed to leave committee as is for present.

Chefs – we need to look at some new chefs for 2017 and perhaps have a northern chef.

Sponsorship - One sponsor was interested in becoming a main sponsor and there was discussion in terms of what would they bring and what would they want for their sponsorship.   There was further discussion on level of cash and in-kind sponsorship potentially on offer and how this might work in terms of other sponsors.  It was agreed that further discussions would be necessary and update brought to next meeting.

Chairman advised that FBD were interested in being a sponsor for 2017

Chairman had discussion with Agri Aware and new CEO will meet Committee to discuss ideas for next year.  We need to promote Farm to Fork approach.

Admission fee/stand fees - It was agreed by members that the admission fee should be €7 and have parking free.  Stand fees are to be increased by €50 (€250 and €450 hot food)

- Taste of Cavan Christmas Market

Members were advised that following on from previous requests to have more Taste of Cavan events, a small Xmas market was proposed for Market Square with 8 wooden huts working in conjunction with Cavan Chamber of Commerce – opening on Fri 16th Dec until Wed 21st Dec.  Some exhibitors from Taste of Cavan had expressed an interest in taking part.

- Any other business

There was some discussion on the BBC Good Food Show, it’s a good show but costs are expensive.  The exhibitors taking part on the Taste of Cavan stand got some contracts to supply businesses in Belfast and Cavan County Council got good publicity for Taste of Cavan and the county – approx 1,000 people entered a competition for overnight stay in St. Kyrans and those contacts will be kept on a database for future communications.

- Date of next meeting

Friday 16th December at 11am (followed by Xmas lunch)

Actions Arising:

- Draft Strategy to go to producers, Economic SPC & TOC committee

- Venue to be booked for 2017

- Overall plan for Taste of Cavan in terms of it being a Regional event

- Launch - suggestions

- Chefs – need some new chefs for 2017

- Charity rules to be developed

- Sponsorship – update on sponsors

- Set up meeting in new year with Agri Aware CEO to discuss ideas for next year

- Xmas Market official opening 16th Dec at 11am