**Meeting of the Cavan Resettlement Interagency Working Group held on 24 September 2020 at 11.30 am online via Microsoft Teams**

**In attendance:** Gráinne Boyle, Social Inclusion, Cavan County Council

Joanne McCabe, Resettlement Worker

Hani Aliwi, Intercultural Worker

Elaine Nolan, Education Welfare Officer

Eoin Doyle – DOS Cavan County Council

Bridie McBrearty, SEO Cavan County Council

Niall McKiernan, An Garda Síochána

Terry Hyland – Breffni Integrated

Elaine Nolan - Education Welfare Officer

**Apologies:** Cathal Grant – TUSLA

Michael Mussi – AO Cavan County Council

Brendan Fitzgerald – Dept Justice

Mary Rose Smith, Primary Care Network Manager, HSE

1. Minutes of previous meeting of 17 September – proposed and approved
2. Update from Department – BF unable to connect to call, BMcB advised that the Department asked that resettlement would take place as soon as possible.
3. Update from Agencies:
   * Mary Rose advised HSE has secured 2 further GP practices and asked that medical notes be transferred to her as soon as possible
   * Niall McKiernan - Gardai – nothing to report
   * DEASP – will have payments organised before arrival
   * EN advised that she was trying to get schools finalised, she will liaise with JMcC in relation to this. It was noted that all pupils were currently attending school.
   * Houses – JMcC/HA had received keys, they are carpeted and furniture will arrive on Tuesday next and houses will be ready for occupation shortly.
4. Resettlement Date – It was agreed that resettlement would be arranged for 6th October.
5. Finalise Arrangements – TH advised that the offices of Breffni Integrated would be used and asked that families enter by back door as this gave direct access to room being used. He will have all Covid 19 measures catered for to ensure a safe registration. It was agreed that in so far as possible all paperwork be finalised by the Agencies prior to this date and was noted staggered arrival has been proposed by Dept.
6. AOB – ED complimented all members of the group of their achievements in getting the project implemented and thanked everybody for their assistance to date.
7. Date of next Meeting: Friday, 2October at11.30 a.m. online via Microsoft Teams.